## Slide 1
Role | Influence (H/M/L) | Interest (H/M/L) | Primary Information Needs | Communication Approach
CEO | H | M | Conversion and sales data, revenue forecasts, ROAS, ROI, historical perspective | Provide overview updates with only the most essential information via email monthly and meetings quarterly
Marketing team | H | H | Engagement and conversion goals and data, campaign strategy, task assignments and deadlines | Communicate all relevant details daily via email and chat and hold weekly meetings
Project manager | M | M | Campaign progress, task assignments and deadlines, scheduling delays, budget constraints | Communicate about campaign progress bi-weekly via email and as needed and hold weekly meetings
Information technology (IT) team | M | L | Software and hardware requirements and issues, data archiving | Keep updated on requirements and issues as needed
External ad agency | M | M | Creative requirements, contractual information, scheduling, budget and payment details | Provide updates via email weekly and as needed and meetings monthly
Stakeholder Analysis

## Slide 2
Inform
Inform and respond to needs
Update
Respond to needs
high
low
high
low
Stakeholder Map
Marketing team
IT team
CEO
Project manager
External ad agency
Interest
med
Influence
med

## Slide 3
Role | Information to Be Shared | Means of Communication
CEO | The number of conversions referred from email were up 2% last month over the previous month. Incremental sales last month exceeded targets by 5%. | Create charts to visualize findings and share in monthly email update.
Marketing team | On social media, ads containing video received 12% higher CTRs than ads without video. Several team members are having difficulty setting up their campaign dashboards in the new analytics tool. Team members will require assistance to implement the software correctly. The designer working on a series of promotional emails for the campaign has just resigned. The first of these emails was supposed to be sent out next week, but will now be delayed. Another designer will need to be assigned the tasks of the designer who left. | Update via email immediately about the promotional email delay and the issue with the new analytics software.
Project manager | The designer working on a series of promotional emails for the campaign has just resigned. The first of these emails was supposed to be sent out next week, but will now be delayed. Another designer will need to be assigned the tasks of the designer who left. | Update via email immediately about the promotional email delay and the issue with the new analytics software.
IT team | Several team members are having difficulty setting up their campaign dashboards in the new analytics tool. Team members will require assistance to implement the software correctly. | Update via email immediately about issue with new software and request assistance
External ad agency | On social media, ads containing video received 12% higher CTRs than ads without video. | Create charts to visualize findings and share in monthly meeting
Communication Plan